People360 — HRIS Blueprint Progress

Desktop + Web · 28 modules (M01–M28)

Updated: 7 September 2026 · Audience: Management, HR, project stakeholders

Desktop = People360 installer (pulse/). Web = Skolaris /people360 (iskolaris-fe + iskolaris-be). Combined = best of both; M01, M05, M07 are desktop Ready (web N/A for M01/M07); M16 is web-only (desktop N/A).

Progress snapshot

| Metric | Count | Notes |
| --- | --- | --- |
| Combined Ready | 4 of 28 | 14.3% of full blueprint — M01, M05, M07, M16 |
| Partial | 9 of 28 | Usable but incomplete on Combined |
| Not yet built | 15 of 28 | No workflow on either product |
| MVP Ready | 4 of 17 | MVP-tier modules marked Ready on Combined |

Visual progress bar (Combined): Ready 4 · Partial 9 · Pending 15.

Last week completed (1–7 September 2026)

| # | Deliverable | Modules | Product | Dates | Status | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| W1 | Payslip send by email | M07 | Desktop | 1–7 Sep | Done | SES API; noreply@skolaris.icct.edu.ph; Payroll Transaction Payslip tab + PDF attach. |

This week — targets (8–14 September 2026)

Target outcome: Payroll imports approved web forms (OT amendment, Job Order/WRF) into the desktop batch instead of re-keying.

| # | Deliverable | Modules | Product | Dates | Depends on | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| W2a | Pull approved ESS forms from People360 web | M05 / M07 | Desktop + Web BE | 8–11 Sep | Pulse API key (employee_requests sync) | GET /pulse-api/v1/employee-requests/sync — desktop local store. |
| W2b | Apply synced forms to payroll batch | M05 / M07 | Desktop | 11–14 Sep | W2a complete | OT amendments, Job Order/WRF → batch lines before compute/post. |

Out of scope this week: recruitment, onboarding workflow (M04 deferred).

September 2026 (after next week)

| Window | Focus | Modules | Outcome |
| --- | --- | --- | --- |
| 15–21 Sep | Payslip + forms hardening | M07, M05 | UAT fixes; sync audit log; installer if needed |
| 22–28 Sep | Leave ↔ payroll tie-in | M06, M05 | Approved web leave in desktop batch; desktop leave lines hardening |
| 29 Sep – 5 Oct | Forms + leave polish | M06, M05 | UAT fixes; approved leave import to batch |

Q4 2026 — MVP gaps & deferred

| Priority | Module | Target window | Notes |
| --- | --- | --- | --- |
| MVP | M12 Separation / clearance | Nov 2026 | Clearance workflow + final pay hooks |
| MVP | M17 / M08 Effective-dated govt tables | Nov–Dec 2026 | Version SSS / PhilHealth / Pag-IBIG |
| MVP | M03 Recruitment | Dec 2026 | If hire-to-retire is in scope |
| MVP | M11 / M13 / M14 Discipline, contractors, OSH | Oct–Dec 2026 | Risk modules |
| Phase 2 | M09, M10, M21–M23 | Dec 2026 | Performance, L&D, faculty eval |
| Phase 3 | M26–M28 | Dec 2026 | Succession, AI advisory, ESG (stretch backlog) |
| Deferred | M04 Onboarding | TBD | Not in current plan — ESS document upload/review stays |

Blueprint stages — high-level targets

| Stage | Target substantially complete | Key milestones |
| --- | --- | --- |
| 1 Foundation | Done (desktop M01) | — |
| 2 Daily HR | Dec 2026 | M16 forms bridge (Sep 2026 W2); M06 web leave Ready |
| 3 Payroll & compliance | Dec 2026 | M07 desktop Ready; M17 (Nov 2026) |
| 4 Risk & outsourcing | Dec 2026 | M11–M14 greenfield |
| 5 Education | Dec 2026 | M19/M20 completion; M21+ phase 2 stretch |
| 6–7 Intelligence / advanced | Dec 2026 | Reporting first; AI/ESG if capacity |

External checklist (this week)

| Item | Owner | Needed for |
| --- | --- | --- |
| Pulse API key: employee_requests list + sync | Skolaris admin | W2a |
| HR: sample approved OT + Job Order in staging | HR | W2b UAT |
| Campus PCs People360 1.0.2+ with HTTPS | Campus IT | W2a |

Desktop Ready — agreed scope (3 modules)

Gaps listed under Web are not desktop owner work.

| ID | Module | Desktop (Ready) | Web (not desktop) |
| --- | --- | --- | --- |
| M01 | Organization & HR Configuration | Campuses, colleges, programs, departments, positions, designations, ranks, employment types, payroll calendar, holidays, users/roles. | Web N/A — org configuration is desktop-only (org chart deferred). |
| M05 | Time, Attendance & Scheduling | Policy, shifts, holidays, time log upload, biometric S3 pull, HR attendance edit, payroll OT, faculty load. | Live clock-in, QR punch, OB, ESS corrections, attendance approval. |
| M07 | Payroll & Statutory Pay | Compute/post, payslips, register, BIR reports, payslip email. | Web N/A — live payroll is desktop-only. |

Full module map — Desktop · Web · Combined

Target date = planned substantially complete (from §10 delivery timeline).

M02 open gap: none on desktop (bank accounts shipped). Web master parity still Partial.

| ID | Module | Priority | Target date | Desktop | Web | Combined |
| --- | --- | --- | --- | --- | --- | --- |
| M01 | Organization & HR Configuration | MVP | Done | Ready | N/A | Ready |
| M02 | Worker / Employee Master Data | MVP | Dec 2026 | Ready | Partial | Partial |
| M03 | Recruitment & Applicant Tracking | MVP | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M04 | Onboarding & Employment Documents | MVP | Deferred | Partial | Partial | Partial |
| M05 | Time, Attendance & Scheduling | MVP | 14 Sep 2026 | Ready | Partial | Ready |
| M06 | Leave & Absence Management | MVP | Oct 2026 | Partial | Ready | Partial |
| M07 | Payroll & Statutory Pay | MVP | Done | Ready | N/A | Ready |
| M08 | Benefits & Government Contributions | MVP | Nov–Dec 2026 | Partial | Not yet built | Partial |
| M09 | Performance Management | Phase 2 | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M10 | Learning & Development | Phase 2 | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M11 | Grievance & Discipline | MVP | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M12 | Separation, Clearance & Retirement | MVP | Nov 2026 | Not yet built | Not yet built | Not yet built |
| M13 | Contractor & Outsourced Workforce | MVP | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M14 | Occupational Safety & Health | MVP | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M15 | Data Privacy & Records | MVP | Dec 2026 | Partial | Partial | Partial |
| M16 | Self-Service, Requests & Approvals | MVP | Done | N/A | Ready | Ready |
| M17 | HR Compliance & Legal Rules | MVP | Nov–Dec 2026 | Partial | Not yet built | Partial |
| M18 | HR Analytics, Dashboards & Audit | Phase 2 | Dec 2026 | Partial | Partial | Partial |
| M19 | Faculty & Academic Personnel | MVP (schools) | Dec 2026 | Partial | Partial | Partial |
| M20 | Faculty Load, Schedule & Overload | MVP (schools) | Dec 2026 | Partial | Partial | Partial |
| M21 | Faculty Evaluation & Promotion | Phase 2 | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M22 | Faculty Development & Research | Phase 2 | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M23 | Student-Safeguarding / Conduct | Phase 2 | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M24 | Sales / Commission & Incentive | Optional | Optional | Not yet built | Not yet built | Not yet built |
| M25 | Shift, Field & Branch Workforce | Optional | Optional | Not yet built | Not yet built | Not yet built |
| M26 | Succession & Workforce Planning | Phase 3 | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M27 | AI Assistance & Automation | Phase 3 | Dec 2026 | Not yet built | Not yet built | Not yet built |
| M28 | SDG / ESG Workforce Reporting | Phase 3 | Dec 2026 | Not yet built | Not yet built | Not yet built |

Related documents

Technical gap analysis + timeline: pulse/docs/hris-blueprint-gap-analysis.md

Progress dashboard (HTML): pulse/docs/People360-HRIS-Blueprint-Progress.html

Stakeholder status report: pulse/docs/People360-HRIS-Blueprint-Status-2026-08-27.html

Blueprint source PDF: pulse/docs/HRIS-Software-Modules-Blueprint-PH.pdf

— End of progress report · 7 September 2026 —